# VELTRIX SPORTS

# Pricing & Application Plan

Date: August 29, 2026
Status: Ready for Review

# 1. PRICING BREAKDOWN

## 1.1 Option A: MVP (2 Weeks) - RECOMMENDED

| Role | Count | Rate/Day | Days | Total |
| --- | --- | --- | --- | --- |
| Flutter Developer | 2 | ₹2,000 | 10 | ₹40,000 |
| Backend Developer | 1 | ₹2,500 | 10 | ₹25,000 |
| Subtotal |  |  |  | ₹65,000 |
| TOTAL |  |  |  | ₹65,000 |

Note: UI/UX is in-house, so no additional cost. AWS Free Tier for 12 months.

## 1.2 Option B: Full Product (1 Month)

| Role | Count | Rate/Day | Days | Total |
| --- | --- | --- | --- | --- |
| Flutter Developer | 2 | ₹2,000 | 22 | ₹88,000 |
| Backend Developer | 1 | ₹2,500 | 22 | ₹55,000 |
| QA Engineer | 1 | ₹1,500 | 15 | ₹22,500 |
| Subtotal |  |  |  | ₹1,65,500 |
| TOTAL |  |  |  | ₹1,70,500 |

## 1.3 Option C: Complete Product (3 Months)

| Role | Count | Rate/Day | Days | Total |
| --- | --- | --- | --- | --- |
| Flutter Developer | 3 | ₹2,000 | 66 | ₹3,96,000 |
| Backend Developer | 2 | ₹2,500 | 66 | ₹3,30,000 |
| QA Engineer | 1 | ₹1,500 | 44 | ₹66,000 |
| DevOps | 1 | ₹2,000 | 22 | ₹44,000 |
| Subtotal |  |  |  | ₹8,36,000 |
| AWS (3 months) |  |  |  | ₹15,000 |
| TOTAL |  |  |  | ₹8,51,000 |

## 1.4 Monthly Running Cost

| Service | Cost/Month |
| --- | --- |
| AWS EC2 | ₹1,400 |
| AWS RDS | ₹2,800 |
| AWS S3 | ₹200 |
| AWS CloudFront | ₹800 |
| Total | ₹5,300/month |

## 1.5 Third-Party Service Costs

| Service | Pricing |
| --- | --- |
| Razorpay | 2% per transaction |
| Firebase | Free (1K notifications/day) |
| Garmin API | Free |
| Apple Developer | ₹7,500/year |
| Google Play | ₹25,000 (one-time) |

# 2. UI/UX DELIVERABLES

## 2.1 Design System

☐ Color palette (Primary, Secondary, Accent)

☐ Typography (Font family, sizes, weights)

☐ Spacing system (Margins, padding)

☐ Border radius

☐ Shadows

☐ Icons style

☐ Button styles

☐ Input field styles

☐ Card styles

## 2.2 Screens Required (15+)

### Auth Screens

☐ Splash Screen

☐ Login Screen

☐ Register Screen

☐ OTP Verification Screen

☐ Forgot Password Screen

### Main Screens

☐ Dashboard Screen

☐ Training Plans List Screen

☐ Plan Detail Screen

☐ Session Detail Screen

☐ Events List Screen

☐ Event Detail Screen

☐ Registration Form Screen

☐ My Registrations Screen

☐ Profile Screen

☐ Settings Screen

### Additional Screens

☐ Payment Checkout Screen

☐ Payment Success Screen

☐ Payment Failure Screen

☐ Error States (404, 500)

☐ Empty States

☐ Loading States

## 2.3 Components Required

☐ App Bar

☐ Bottom Navigation

☐ Side Drawer

☐ Cards (Event, Plan, Session)

☐ Buttons (Primary, Secondary, Text)

☐ Input Fields

☐ Dropdowns

☐ Badges

☐ Avatars

☐ Progress Indicators

☐ Modals/Bottom Sheets

☐ Toast/Snackbar

## 2.4 Prototypes Required

☐ Login flow prototype

☐ Registration flow prototype

☐ Dashboard flow prototype

☐ Training plan flow prototype

☐ Event registration flow prototype

☐ Payment flow prototype

# 3. FEATURE LIST (FROM PDF)

## 3.1 Authentication Module

| Feature | Priority | MVP |
| --- | --- | --- |
| User Registration (Email) | P0 | Yes |
| User Registration (Phone) | P0 | Yes |
| User Login | P0 | Yes |
| OTP Verification | P0 | Yes |
| Forgot Password | P1 | No |
| Social Login (Google) | P1 | No |
| Social Login (Apple) | P1 | No |
| Remember Me | P2 | No |

## 3.2 Training Plans Module

| Feature | Priority | MVP |
| --- | --- | --- |
| View Training Plans | P0 | Yes |
| Plan Detail View | P0 | Yes |
| Session Detail View | P0 | Yes |
| Complete Session | P0 | Yes |
| Create Training Plan | P1 | No |
| AI Plan Generation | P2 | No |
| Progress Dashboard | P1 | No |
| Training Calendar | P2 | No |

## 3.3 Events Module

| Feature | Priority | MVP |
| --- | --- | --- |
| Browse Events | P0 | Yes |
| Event Detail View | P0 | Yes |
| Filter Events | P0 | Yes |
| Search Events | P1 | No |
| Event Registration | P0 | Yes |
| My Registrations | P1 | No |
| Event Reviews | P2 | No |
| Event Sharing | P2 | No |

## 3.4 Ticketing Module

| Feature | Priority | MVP |
| --- | --- | --- |
| Browse Marketplace | P1 | No |
| Buy Tickets | P1 | No |
| View My Tickets | P1 | No |
| QR Code Display | P1 | No |
| QR Check-in | P2 | No |
| Promo Codes | P2 | No |
| Refund Request | P2 | No |

## 3.5 Payments Module

| Feature | Priority | MVP |
| --- | --- | --- |
| Razorpay Integration | P0 | Yes |
| UPI Payment | P0 | Yes |
| Card Payment | P0 | Yes |
| Net Banking | P1 | No |
| Payment History | P1 | No |
| Refund Processing | P2 | No |

# 4. MVP SCOPE (2 WEEKS)

## 4.1 Must Build (P0)

✓ User Registration

✓ User Login

✓ OTP Verification

✓ Dashboard

✓ Training Plans List

✓ Plan Detail

✓ Events List

✓ Event Detail

✓ Event Registration

✓ Basic Payment

## 4.2 Skip for MVP

✗ AI Plan Generation

✗ Device Sync

✗ Ticketing Marketplace

✗ Admin Panel

✗ Analytics

# 5. DEVELOPMENT TIMELINE

## Week 1: Foundation

| Day | Backend | Frontend |
| --- | --- | --- |
| Day 1 | Setup Node.js, PostgreSQL, Auth APIs | Flutter project setup |
| Day 2 | OTP, JWT, User APIs | API client, Auth BLoC |
| Day 3 | Plan APIs | Auth screens |
| Day 4 | Event APIs | Dashboard screen |
| Day 5 | Payment APIs | Training plans screens |

## Week 2: Features

| Day | Backend | Frontend |
| --- | --- | --- |
| Day 6 | Testing, Bug fixes | Events screens |
| Day 7 | Documentation | Registration form |
| Day 8 | Deployment setup | Payment integration |
| Day 9 | AWS setup | Testing, Bug fixes |
| Day 10 | Final testing | Build, Deploy |

# 6. TEAM RESPONSIBILITIES

## UI/UX Team

☐ Design system creation

☐ All screen designs (15+ screens)

☐ Prototypes (6 flows)

☐ Asset export (icons, images)

☐ Design handoff to developers

## Backend Team

☐ API development (10+ endpoints)

☐ Database setup (PostgreSQL)

☐ Authentication (JWT, OTP)

☐ Payment integration (Razorpay)

☐ Deployment (AWS)

## Frontend Team

☐ Flutter app development

☐ Screen implementation (15+ screens)

☐ State management (BLoC)

☐ API integration

☐ Testing on Android & iOS

# 7. SUCCESS CRITERIA

☐ User can register with email/phone

☐ User can login

☐ User can see dashboard

☐ User can browse training plans

☐ User can view plan details

☐ User can browse events

☐ User can view event details

☐ User can register for events

☐ User can make payment

☐ App works on Android & iOS

# 8. APPROVAL

| Role | Signature |
| --- | --- |
| Project Manager | _______________ |
| Tech Lead | _______________ |
| UI/UX Lead | _______________ |
| Stakeholder | _______________ |